Present:

Cllr Rob Marsh-Feiley, Iain Gibson, Caroline Abbott, Miche Henri, Kevin Prior, Graham Thornett, Langton Brook Consultants represented by Andy Robinson. 1. Apologies – Colin Ablitt, Sarah Foote 2. The purpose of the meeting was to discuss the comments received from the representatives of the two sites, E and F, in response to the masterplan and to agree any amendments.

3. Following consideration of the comments received and discussion thereon, it was agreed that: the two barns on site E should be removed from the allocation and not included in the total number of dwellings a maximum of three units to be situated on the southern side of the new access road leading west off Denham Road to replace the substantial planting on the south boundary with block planting to allow views out of the site, but not to allow dwellings to be built between the block planting any land transferred to the school must be gifted and free of any caveats 4. It was confirmed that this brings the total number of dwellings for the sites to 38 on site E, not including the barns, and 15 on site F, a total of 53 dwellings. The number of dwellings required by SCC is stipulated as 43; 30 designated for site E and 13 around the village with planning approval. The 53 is therefore more than adequate for what is required. 5. It was confirmed that with an NDP in the process of being adopted, it would be very difficult for any planning applications to be granted on land outside of the settlement boundary. This would in effect protect the poly focal nature of Hoxne. Infilling within the settlement boundary would probably be allowed. 6. The timeframe for the adoption of the NDP was outlined as follows: publish pre-submission draft at the end of October 2021 six weeks for comments review comments and make any changes if there are any substantial changes to be made, publish a new pre-submission draft if no substantial changes, plan to be submitted to District Council around February 2022 examination by District Council to take place publish submission draft for formal comment for 6 weeks – April to mid-May 2022 examination to take place in summer 2022 hold referendum in early autumn 2022 The meeting was closed at 20:30